## Gantt Diagram
Project: | PID Control of a DC Motor
Team members: | Francisco Javier Tapía |  | Mabe, UTEQ
| Juan Luis Nepomuceno |  | Mabe
| Irvin Ramírez |  | Mabe
Project Start Date: |  | 2019-08-16 |  |  | Friday | FW 33
Project End Date: |  | 2019-10-26 |  |  | Saturday | FW 43 |  |  |  | AUGUST | [15 empty] | SEPTEMBER | [29 empty] | OCTOBER
Project Delivery Date: |  | 2019-10-31 |  |  | Thursday | FW 44 |  |  |  | FW 33 |  |  | FW 34 | [6 empty] | FW 35 | [6 empty] | FW 36 | [6 empty] | FW 37 | [6 empty] | FW 38 | [6 empty] | FW 39 | [6 empty] | FW 40 | [6 empty] | FW 41 | [6 empty] | FW 42 | [6 empty] | FW 43 | [6 empty] | FW 44
[10 empty] | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
ITEM | TASK |  |  | LEAD | START | END | DAYS | % DONE | WORK DAYS | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
1 | Requirements Revision |  |  | All | 2019-08-16 | 2019-08-18 | 3 | 100 | 2 | bar: FW 33 16 F to FW 33 18 S
2 | Planning |  |  | All | 2019-08-19 | 2019-09-01 | 14 | 100 | 4 | bar: FW 34 19 M to FW 35 1 S
3 | Risk Analysis |  |  | All | 2019-08-19 | 2019-09-01 | 14 | 100 | 4 | bar: FW 34 19 M to FW 35 1 S
4 | AMEF |  |  | Francisco | 2019-08-19 | 2019-09-01 | 14 | 100 | 4 | bar: FW 34 19 M to FW 35 1 S
5 | General Design Based on Requirements |  |  | Juan, Irvin | 2019-08-19 | 2019-09-13 | 56 | 100 | 16 | bar: FW 34 19 M to FW 41 13 S
6 | ADC Initialization |  |  | Irvin | 2019-09-09 | 2019-09-15 | 7 | 100 | 2 | bar: FW 37 9 M to FW 37 15 S
7 | ADC Initialization Test |  |  | Juan | 2019-09-09 | 2019-09-15 | 7 | 100 | 2 | bar: FW 37 9 M to FW 37 15 S
8 | PWM Initialization |  |  | Juan | 2019-09-16 | 2019-09-22 | 7 | 100 | 2 | bar: FW 38 16 M to FW 38 22 S
9 | PWM Initialization Test |  |  | Irvin | 2019-09-16 | 2019-09-22 | 7 | 100 | 2 | bar: FW 38 16 M to FW 38 22 S
10 | Input Capture Initialization |  |  | Irvin | 2019-09-30 | 2019-09-13 | 14 | 100 | 4 | bar: FW 40 30 M to FW 41 13 S
11 | Input Capture Initialization Test |  |  | Juan | 2019-09-30 | 2019-09-13 | 14 | 100 | 4 | bar: FW 40 30 M to FW 41 13 S
12 | System Integration (ADC, PWM and Input Capture) |  |  | All | 2019-09-16 | 2019-09-29 | 14 | 100 | 4 | bar: FW 38 16 M to FW 39 29 S
13 | PID Implementation |  |  | Irvin | 2019-09-30 | 2019-10-13 | 14 | 100 | 4 | bar: FW 40 30 M to FW 41 13 S
14 | System Integration (without GUI) |  |  | Irvin | 2019-10-07 | 2019-10-20 | 14 | 100 | 4 | bar: FW 41 7 M to FW 42 20 S
15 | Display Initialization |  |  | Juan, Irvin | 2019-10-14 | 2019-10-27 | 14 | 100 | 4 | bar: FW 42 14 M to FW 43 27 S
16 | Display Initialization Test |  |  | Francisco | 2019-10-14 | 2019-10-27 | 14 | 100 | 4 | bar: FW 42 14 M to FW 43 27 S
17 | GUI Design |  |  | Juan | 2019-10-14 | 2019-10-27 | 14 | 100 | 4 | bar: FW 42 14 M to FW 43 27 S
18 | System Integration (with GUI) |  |  | Irvin | 2019-10-14 | 2019-10-27 | 14 | 100 | 4 | bar: FW 42 14 M to FW 43 27 S
19 | Black Box Test |  |  | All | 2019-09-16 | 2019-10-27 | 42 | 100 | 12 | bar: FW 38 16 M to FW 43 27 S
20 | HW/SW Revision |  |  | All | 2019-09-16 | 2019-10-27 | 42 | 100 | 12 | bar: FW 38 16 M to FW 43 27 S
21 | Final Released |  |  | All | 2019-10-14 | 2019-10-27 | 14 | 100 | 4 | bar: FW 42 14 M to FW 43 27 S
22 | Final Project Delivery |  |  | All | 2019-10-28 | 2019-10-31 | 4 | 100 | 1 | bar: FW 44 28 M to FW 44 31 T